## Project Charter
Generated by the PlausibleBA Skills Library ¦ www.plausibleba.com
EgyGlass - Project Management Plan
ERP Internal System ¦ v1.0
Item | Detail
Project Name | EgyGlass Internal Management System (ERP)
Sponsor | EgyGlass Executive Management
PM | TBD
Start | Q1 2026
Target Completion | Q4 2026
Duration | ~10 months (4 phases)
Success Criteria | All 7 modules live, all 6 departments using system, Excel eliminated

## WBS
Generated by the PlausibleBA Skills Library ¦ www.plausibleba.com
EgyGlass - Work Breakdown Structure
Task Hierarchy
# | Level | Task Name | Assigned To | Duration
1 | L1 | Project Initiation
1.1 | L2 | Requirements Gathering
1.1.1 | L3 | Stakeholder interviews
1.1.2 | L3 | Current process documentation
1.1.3 | L3 | BRD specification
1.2 | L2 | System Design
1.2.1 | L3 | Architecture design
1.2.2 | L3 | Database schema
1.2.3 | L3 | UI/UX wireframes
2 | L1 | Phase 1: Core Modules
2.1 | L2 | CRM Module
2.1.1 | L3 | Customer management
2.1.2 | L3 | Lead & pipeline
2.1.3 | L3 | Quotation engine
2.2 | L2 | Survey Module
2.2.1 | L3 | Survey request & scheduling
2.2.2 | L3 | Measurement recording
2.3 | L2 | Technical Office Module
2.3.1 | L3 | Drawing management
2.3.2 | L3 | Pricing & BOM
3 | L1 | Phase 2: Operations
3.1 | L2 | Procurement & Inventory
3.1.1 | L3 | Order management
3.1.2 | L3 | Inventory tracking
3.2 | L2 | Installation Module
3.2.1 | L3 | Scheduling & team assignment
3.2.2 | L3 | Mobile app for installers
4 | L1 | Phase 3: Finance
4.1 | L2 | Accounting Module
4.1.1 | L3 | E-invoicing integration
4.1.2 | L3 | Payment tracking
4.1.3 | L3 | Account statements
5 | L1 | Phase 4: Advanced
5.1 | L2 | Dashboard & Analytics
5.2 | L2 | External Integrations
6 | L1 | Testing & Deployment
6.1 | L2 | Unit & integration testing
6.2 | L2 | UAT
6.3 | L2 | Training & documentation
6.4 | L2 | Go-live & hypercare

## Risk Register
Generated by the PlausibleBA Skills Library ¦ www.plausibleba.com
EgyGlass - Risk Register
Project Risk Assessment
ID | Risk | Description | Probability | Impact | Severity | Mitigation
R1 | Scope creep | Additional requirements during dev | High | High | Critical | Freeze scope; change control
R2 | User adoption resistance | Staff reluctant to leave Excel | High | Medium | High | Training; champion program
R3 | Data migration issues | Inconsistent Excel data | Medium | High | High | Data audit before migration
R4 | Tech complexity | E-invoicing integration | Medium | Medium | Medium | Early prototyping
R5 | Resource availability | Key members unavailable | Medium | Medium | Medium | Cross-training
R6 | Mobile app challenges | Installers struggle with app | Low | Medium | Medium | Simple UI; offline-first
R7 | Budget overrun | Dev takes longer | Medium | High | High | Buffer; phased approach