## Quality & Operations
Generated by the PlausibleBA Skills Library ¦ www.plausibleba.com
EgyGlass - Quality & Operations
Quality Gates & Operational Processes
1. Quality Gates
Gate | Name | When | Check Items | Responsible
QG1 | Survey Review | Before tech office handoff | Completeness, photo quality | Survey Supervisor
QG2 | Design Review | Before factory | Drawing accuracy, BOM | Technical Manager
QG3 | Order Review | Before manufacturing | All components present | Reviewer
QG4 | Pre-Install Check | Before team dispatched | Products ready, docs in order | Warehouse
QG5 | Post-Install Inspection | After installation | Quality, photos, satisfaction | Install Manager
QG6 | Invoice Review | Before sending | Amounts, adjustments, VAT | Accountant
2. Operational Processes
Process | Owner | Frequency | Activities
Survey Scheduling | Surveyor | Daily | Calendar, customer confirmation, route
Tech Review Meeting | Tech Manager | Weekly | Review queue, resolve issues
Inventory Count | Warehouse | Weekly | Physical vs system, adjust
Install Planning | Install Manager | Daily | Schedule, assign teams, check readiness
Management Review | All Managers | Weekly | KPI review, decisions
Customer Follow-up | Sales Reps | Daily | Pipeline review, call prospects
3. Additional Items (Adjustments)
Item Type | Cause | Source | Cost Responsibility
Sandpaper (صنفرة) | Manufacturing defect | Production | Factory
Breakage (بدل كسر) | Glass broken | Install/Warehouse | Project
Mfg Error (خطأ تصنيع) | Wrong size/spec | Factory | Factory cost
Design Error (خطأ مكتب) | Wrong measurement/design | Tech Office | Tech cost
Customer Delay (تأجيل) | Customer postponed | Customer | Reschedule fee
Modification (تعديل) | Customer changes | Customer | Additional cost